## Dashboard
REAL ESTATE CRM - ULTRA FIX TRACKER
ISSUE SUMMARY
Category | Critical | High | Medium | Low | Total | Status
Build & TypeScript | 4 | 5 | 3 | 2 | 14 | BLOCKED
Backend API | 5 | 5 | 8 | 10 | 28 | CRITICAL
Frontend React | 2 | 4 | 4 | 3 | 13 | NEEDS FIX
Security | 8 | 4 | 3 | 2 | 17 | CRITICAL
Database | 4 | 4 | 4 | 1 | 13 | NEEDS FIX
Infrastructure | 2 | 3 | 4 | 3 | 12 | NEEDS FIX
Testing | 0 | 2 | 3 | 2 | 7 | GAPS
TOTALS | 25 | 27 | 29 | 23 | 104
FIX PRIORITY ORDER
# | Task | Description | Category
1 | Platform Dependencies | Run pnpm install on Linux to get correct binaries | Build
2 | Prisma Schema Validation | Fix schema errors and regenerate client | Database
3 | Security Hardcoded Secrets | Replace all hardcoded secrets with env vars | Security
4 | TypeScript Compilation | Fix all 23 TS errors for clean build | Build
5 | SQL Injection Fix | Parameterize all raw SQL in buyer-pool.ts | Security
6 | XSS Vulnerability | Add DOMPurify to articles-management.tsx | Security
7 | Hardcoded localhost URL | Replace localhost in App.tsx with env var | Frontend
8 | Missing Auth on Endpoints | Add auth middleware to unprotected routes | Backend
9 | Database Indexes | Add missing indexes on properties, accounts | Database
10 | Error Handling | Add try-catch to all async route handlers | Backend

## All Issues
ID | Severity | Category | Subcategory | Issue Title | Description | File Path | Line(s) | Suggested Fix | Status | Assigned To | Notes
B-001 | CRITICAL | Build | Dependencies | Rollup Linux binary missing | node_modules installed on macOS but running on Linux - @rollup/rollup-linux-arm64-gnu not found | node_modules/ | - | Run pnpm install on Linux target platform | Open
B-002 | CRITICAL | Build | Dependencies | esbuild platform mismatch | @esbuild/darwin-arm64 present but needs @esbuild/linux-arm64 | node_modules/ | - | Run pnpm install on Linux target platform | Open
B-003 | CRITICAL | Build | Prisma | Prisma validation fails | Prisma engines not installed for linux-arm64, 403 on binary download | data/schema/prisma/schema.prisma | - | Run npx prisma generate on target platform | Open
B-004 | HIGH | Build | Prisma | Deprecated prisma config in package.json | package.json#prisma is deprecated, will be removed in Prisma 7 | package.json | - | Migrate to prisma.config.ts | Open
B-005 | HIGH | TypeScript | Type Error | Optional string assigned to required field | auth.id may be undefined but assigned to required string fields | apps/api/routes/cms-articles.ts | 136 | Add null check: if (!req.auth?.id) return res.status(401) | Open
B-006 | HIGH | TypeScript | Type Error | CMS Landing undefined assignments (12 instances) | Multiple properties expect string but receive string¦undefined | apps/api/routes/cms-landing.ts | 127-349 | Add non-null assertions or default values | Open
B-007 | HIGH | TypeScript | Type Error | Missing properties on Prisma result | listingType and propertyType not in query select | apps/api/routes/listings.ts | 180, 224 | Add fields to Prisma select clause | Open
B-008 | MEDIUM | TypeScript | Type Error | Variable redeclaration in seed scripts | BASE constant redeclared across seed files | apps/api/scripts/seed-saudi-*.ts | 13-15 | Rename to unique constants or use module scope | Open
B-009 | MEDIUM | TypeScript | Type Error | Duplicate main() function | Both seed scripts declare main() in same compilation unit | apps/api/scripts/seed-saudi-*.ts | 45-46 | Use separate tsconfig for scripts | Open
B-010 | HIGH | TypeScript | Type Error | Missing prisma module import | Cannot find module ../lib/prisma | apps/api/src/services/pool.service.ts | 1 | Create lib/prisma.ts or fix import path | Open
B-011 | MEDIUM | TypeScript | Type Error | Express Request user type mismatch | Subsequent property declarations must have same type | apps/api/src/middleware/auth.middleware.ts | 25 | Unify Express.Request user type declarations | Open
B-012 | HIGH | TypeScript | Type Error | Toaster component spread error | Rest types may only be created from object types | apps/web/src/components/ui/toaster.tsx | 16 | Fix destructuring pattern with proper typing | Open
B-013 | MEDIUM | TypeScript | Type Error | Unknown type in CMS landing page | unknown not assignable to LandingSection | apps/web/src/pages/admin/cms-landing/index.tsx | 113, 140 | Add proper type assertions or generics | Open
B-014 | MEDIUM | TypeScript | Type Error | Non-existent props on components | className on Toast, emptyMessage on AdminTable, className on MetricCard | apps/web/src/pages/admin/moderation.tsx, dashboard.tsx | 36, 198, 282 | Add missing props to component interfaces or remove usage | Open
S-001 | CRITICAL | Security | Credentials | Hardcoded admin credentials | Default admin user/pass: admin/admin123 in auth route | apps/api/routes/auth.ts | 137 | Remove hardcoded defaults, require env vars | Open
S-002 | CRITICAL | Security | Credentials | Hardcoded secrets in Docker Compose | JWT_SECRET and SESSION_SECRET have placeholder values | docker-compose.yml | - | Use Docker secrets or external secret manager | Open
S-003 | CRITICAL | Security | Credentials | PM2 config weak secret fallback | JWT_SECRET defaults to change-me | ecosystem.config.js | - | Fail-fast if secrets not set | Open
S-004 | CRITICAL | Security | SQL Injection | Raw SQL with string interpolation | $queryRawUnsafe with WHERE clause from user input | apps/api/routes/buyer-pool.ts | 120-126 | Use parameterized queries or Prisma query builder | Open
S-005 | CRITICAL | Security | Auth | Admin reset endpoint too accessible | /api/auth/ensure-primary-admin with weak token check | apps/api/routes/auth.ts | 126-178 | Add IP allowlist, strong token, disable in production | Open
S-006 | CRITICAL | Security | XSS | dangerouslySetInnerHTML without sanitization | Article content rendered without DOMPurify | apps/web/src/pages/admin/articles-management.tsx | 854 | Import and apply DOMPurify.sanitize() | Open
S-007 | CRITICAL | Security | CSP | Overly permissive Content Security Policy | CSP allows unsafe-inline scripts | apps/api/index.ts | - | Use nonces or hashes instead of unsafe-inline | Open
S-008 | CRITICAL | Security | Infrastructure | Public Cloud Run unauthenticated access | --allow-unauthenticated exposes entire API | deploy-gcp.sh | - | Use IAP or API gateway for auth layer | Open
S-009 | HIGH | Security | Token | Timing attack on preview token | String comparison vulnerable to timing attacks | apps/api/routes/landing.ts | 27-39 | Use crypto.timingSafeEqual for comparison | Open
S-010 | HIGH | Security | Error Handling | Stack traces exposed in dev mode | Error messages may leak DB connection strings | apps/api/middleware/errorHandler.ts | 54-57 | Sanitize error messages even in dev mode | Open
S-011 | HIGH | Security | Rate Limiting | Auth rate limit too permissive | 100 attempts in 15 min is too high | apps/api/index.ts | - | Reduce to 10-20 attempts, add progressive lockout | Open
S-012 | HIGH | Security | Rate Limiting | Admin routes skip rate limiting | /api/rbac-admin/ and /api/cms/ exempted | apps/api/routes.ts | 165 | Apply stricter rate limiting to admin routes | Open
S-013 | MEDIUM | Security | CORS | GCS bucket allows wildcard origin | Cloud Storage CORS set to * with all methods | setup-cloud-sql.sh | - | Restrict to specific allowed origins | Open
S-014 | MEDIUM | Security | Infrastructure | DB password in Terraform plaintext | Cloud SQL password in environment variables | terraform/main.tf | - | Use Secret Manager references | Open
S-015 | MEDIUM | Security | PII | No encryption for PII fields | Emails, phone numbers stored in plaintext | data/schema/prisma/schema.prisma | - | Add field-level encryption for sensitive data | Open
S-016 | LOW | Security | Session | Session cookie TTL too short | Session set to 5 minutes - poor UX | apps/api/index.ts | - | Increase to 30-60 minutes with sliding window | Open
S-017 | LOW | Security | Audit | Missing audit logs on admin endpoints | Admin setup and impersonate lack audit trail | apps/api/routes/auth.ts | - | Add audit logging middleware | Open
A-001 | HIGH | Backend | Auth | Missing auth on health endpoint | /api/pool/health returns DB counts without auth | apps/api/routes/buyer-pool.ts | 62-76 | Add authentication middleware | Open
A-002 | HIGH | Backend | Auth | Missing authorization on appointments | No ownership check - any user can create for any customer | apps/api/routes/appointments.ts | 46-73 | Verify customer belongs to user organization | Open
A-003 | HIGH | Backend | Auth | Missing authorization on support tickets | Any authenticated user can update any ticket | apps/api/routes/support.ts | 77-96 | Add ownership/role verification | Open
A-004 | HIGH | Backend | Auth | Seed endpoint exposed without auth | /seed creates test data without requiring admin | apps/api/routes/support.ts | 131-180 | Restrict to development or require admin role | Open
A-005 | HIGH | Backend | Error Handling | Missing try-catch in route handlers | Multiple PUT/DELETE handlers lack error handling | apps/api/routes/support.ts | 79 | Wrap all async handlers in try-catch | Open
A-006 | MEDIUM | Backend | Validation | Missing input validation on POST/PUT | Direct req.body usage without Zod validation | apps/api/routes/support.ts | 79-96 | Add Zod schemas for all mutation endpoints | Open
A-007 | MEDIUM | Backend | Validation | Missing price range validation | minPrice/maxPrice not validated for negative/NaN | apps/api/routes/buyer-pool.ts | 81-88 | Add number validation and bounds checking | Open
A-008 | MEDIUM | Backend | Performance | Unbounded query allows 10K records | pageSize >= 10000 triggers fetch-all mode | apps/api/routes/listings.ts | 76-82 | Set hard maximum limit (e.g., 500) | Open
A-009 | MEDIUM | Backend | Types | Excessive any type usage | req: any, res: any across multiple route files | apps/api/routes/*.ts | Multiple | Replace with proper Express types | Open
A-010 | MEDIUM | Backend | Auth | Organization isolation not enforced | No middleware verifying org membership on data access | apps/api/middleware/ | - | Add org-scoping middleware for all data routes | Open
A-011 | MEDIUM | Backend | Consistency | Inconsistent error response formats | Different error shapes across routes | apps/api/routes/*.ts | Multiple | Standardize with error response utility | Open
A-012 | LOW | Backend | Logging | Console.log instead of structured logger | Direct console calls in auth, rbac-admin, unverified-listings | apps/api/routes/auth.ts, rbac-admin.ts | Multiple | Use logger utility consistently | Open
A-013 | LOW | Backend | Code Quality | Deprecated code left in source | Old schema marked DEPRECATED but still in file | apps/api/routes/unverified-listings.ts | 29-69 | Move to docs or remove entirely | Open
A-014 | LOW | Backend | Config | Preview token cached at module load | process.env read once, never refreshed | apps/api/routes/landing.ts | 6 | Read env var on each request | Open
A-015 | LOW | Backend | CSV | CSV route stub not implemented | Endpoint exists but returns stub response | apps/api/routes/csv.ts | 6-17 | Implement or remove the endpoint | Open
F-001 | CRITICAL | Frontend | URL | Hardcoded localhost breaks production | window.location.href = http://localhost:3000 | apps/web/src/App.tsx | 538 | Use import.meta.env.VITE_API_HOST or window.location.origin | Open
F-002 | CRITICAL | Frontend | XSS | dangerouslySetInnerHTML without sanitization | Article content not sanitized (blog.tsx does sanitize) | apps/web/src/pages/admin/articles-management.tsx | 854 | Add DOMPurify.sanitize() wrapper | Open
F-003 | HIGH | Frontend | Accessibility | Missing alt text on avatar images | Empty alt attribute on user avatars | apps/web/src/pages/platform/forum/index.tsx | 495 | Add descriptive alt text: user.name + avatar | Open
F-004 | HIGH | Frontend | Accessibility | Missing alt text on logo | Logo image lacks proper alt text | apps/web/src/components/landing/LandingFooter.tsx | - | Add alt="Company Name Logo" | Open
F-005 | HIGH | Frontend | Logging | Console.log in production code | Debug logging left in landing, maps, hooks | apps/web/src/pages/landing.tsx, PropertiesMap.tsx, useListingData.ts | Multiple | Wrap in import.meta.env.DEV or remove | Open
F-006 | HIGH | Frontend | Null Safety | Potential undefined in MediaSelector | Alt text could display undefined if DB null | apps/web/src/components/cms/MediaSelector.tsx | 167, 190 | Add fallback: alt={item.altText ¦¦ "Media"} | Open
F-007 | MEDIUM | Frontend | Navigation | window.location.href instead of SPA routing | Full page reload instead of Wouter navigation | apps/web/src/components/listings/ListingCard.tsx | 66 | Use setLocation() from Wouter | Open
F-008 | MEDIUM | Frontend | Navigation | window.location.href in PublicHeader | Another full page reload breaking SPA | apps/web/src/components/layout/PublicHeader.tsx | - | Use setLocation() from Wouter | Open
F-009 | MEDIUM | Frontend | UX | alert() instead of toast notifications | Native browser alerts break UX consistency | ListingCard.tsx, LoginForm.tsx, listing/index.tsx | Multiple | Replace with toast.success()/toast.error() | Open
F-010 | MEDIUM | Frontend | Memory | Object URL memory leak | Image preview URLs not cleaned up | apps/web/src/components/modals/add-property-drawer.tsx | 129 | Add URL.revokeObjectURL in useEffect cleanup | Open
F-011 | LOW | Frontend | Code Quality | Oversized component files | Components with 800-1600 lines need splitting | unverified-listing/index.tsx, articles-management.tsx | - | Extract sub-components | Open
F-012 | LOW | Frontend | Types | Missing nullable checks in hooks | Potential undefined access in useListingData | apps/web/src/hooks/useListingData.ts | - | Add optional chaining and fallbacks | Open
F-013 | LOW | Frontend | Accessibility | Avatar alt text semantics | Alt text doesn't describe the image content | apps/web/src/pages/platform/forum/index.tsx | - | Use format: "{User Name}'s profile photo" | Open
D-001 | CRITICAL | Database | Indexes | Missing index on properties.agentId | Critical for agent property lookups | data/schema/prisma/schema.prisma | - | Add @@index([agentId]) | Open
D-002 | CRITICAL | Database | Indexes | Missing index on properties.organizationId | Critical for org-scoped queries | data/schema/prisma/schema.prisma | - | Add @@index([organizationId]) | Open
D-003 | CRITICAL | Database | Indexes | Missing indexes on properties.city/district/status | Core search/filter fields without indexes | data/schema/prisma/schema.prisma | - | Add composite index @@index([status, city]) | Open
D-004 | CRITICAL | Database | Relations | Broken FK on properties.agentId | No @relation definition for agent reference | data/schema/prisma/schema.prisma | - | Add proper @relation with foreign key | Open
D-005 | HIGH | Database | Indexes | Missing index on accounts.parentAccount | Tree queries will be slow | data/schema/prisma/schema.prisma | - | Add @@index([parentAccount]) | Open
D-006 | HIGH | Database | Indexes | Missing index on accounts.status | Frequent filter field | data/schema/prisma/schema.prisma | - | Add @@index([status]) | Open
D-007 | HIGH | Database | Relations | Missing FK on audit_logs.userId | No referential integrity on audit log user | data/schema/prisma/schema.prisma | - | Add @relation to users model | Open
D-008 | HIGH | Database | Relations | Missing FK on buyer_requests.createdByUserId | No referential integrity | data/schema/prisma/schema.prisma | - | Add @relation to users model | Open
D-009 | MEDIUM | Database | Validation | No format constraints on contact fields | Mobile, email, phone lack regex validation | data/schema/prisma/schema.prisma | - | Add application-level validation via Zod | Open
D-010 | MEDIUM | Database | Indexes | Missing compound indexes for search | Common multi-field queries lack compound indexes | data/schema/prisma/schema.prisma | - | Add @@index([status, city, propertyType]) | Open
D-011 | MEDIUM | Database | Timestamps | Inconsistent timestamp handling | Some models use DateTime, others use String for dates | data/schema/prisma/schema.prisma | - | Standardize on DateTime with @default(now()) | Open
D-012 | MEDIUM | Database | Performance | Missing pagination limits | No DB-level default limit on large tables | apps/api/routes/*.ts | - | Add default LIMIT in all findMany queries | Open
D-013 | LOW | Database | Schema | Orphan models without relations | Some models exist without any foreign key references | data/schema/prisma/schema.prisma | - | Review and add missing relations or remove unused models | Open
I-001 | CRITICAL | Infrastructure | Docker | Docker container no health check | No HEALTHCHECK instruction in Dockerfile | Dockerfile | - | Add HEALTHCHECK CMD curl --fail http://localhost:3000/health | Open
I-002 | CRITICAL | Infrastructure | CI/CD | No vulnerability scanning in pipeline | Cloud Build has no security scan step | cloudbuild.yaml | - | Add npm audit and container scanning step | Open
I-003 | HIGH | Infrastructure | Docker | Floating Node.js version | Uses node:20-alpine - could break on minor updates | Dockerfile | - | Pin to specific version: node:20.11.1-alpine | Open
I-004 | HIGH | Infrastructure | Docker | pnpm lockfile not used in build | Dockerfile uses npm ci instead of pnpm | Dockerfile | - | Switch to pnpm install --frozen-lockfile | Open
I-005 | HIGH | Infrastructure | Terraform | State files unencrypted locally | No remote backend with encryption configured | terraform/main.tf | - | Configure GCS backend with encryption | Open
I-006 | MEDIUM | Infrastructure | Config | ESLint only lints JS/JSX files | TypeScript files completely excluded from linting | eslint.config.js | - | Add TypeScript plugin and extend to .ts/.tsx | Open
I-007 | MEDIUM | Infrastructure | Config | Hardcoded port in Vite dev plugin | Port 3000 hardcoded instead of using env | vite.config.ts | - | Use process.env.PORT ¦¦ 3000 | Open
I-008 | MEDIUM | Infrastructure | Deploy | Cloud Run hardcodes port 8080 | Deployment script uses fixed port | deploy-gcp.sh | - | Use PORT env var consistently | Open
I-009 | MEDIUM | Infrastructure | Config | Missing .env.example for developers | New devs don't know required env vars | Root | - | Create comprehensive .env.example | Open |  | .env.dev.example exists but may be incomplete
I-010 | LOW | Infrastructure | Config | Missing Node.js version in package.json | No engines field specifying required Node version | package.json | - | Add "engines": {"node": ">=20.0.0"} | Open
I-011 | LOW | Infrastructure | Config | ESLint no-console rule disabled | Console.log not flagged during linting | eslint.config.js | - | Enable no-console: warn | Open
I-012 | LOW | Infrastructure | Deploy | Complex build scripts hard to diagnose | Multiple nested shell scripts for deployment | deploy-*.sh | - | Consolidate into documented Makefile | Open
T-001 | HIGH | Testing | Coverage | Only 1 unit test file exists | analytics.test.ts is the only unit test | apps/api/src/routes/__tests__/ | - | Add unit tests for all route modules | Open
T-002 | HIGH | Testing | E2E | Smoke test is minimal (3 tests) | Only checks basic page loads | e2e/smoke.spec.ts | - | Add auth flow, CRUD, and error scenario tests | Open
T-003 | MEDIUM | Testing | Coverage | No auth/RBAC tests | Critical security paths untested | - | - | Add comprehensive auth and permission tests | Open
T-004 | MEDIUM | Testing | Coverage | No API integration tests | Route handlers never tested end-to-end | - | - | Add supertest-based integration tests | Open
T-005 | MEDIUM | Testing | Config | Test references non-existent setup file | Test infrastructure incomplete | apps/api/src/routes/__tests__/ | - | Create proper test setup with mocks | Open
T-006 | LOW | Testing | Coverage | No frontend component tests | React components have zero test coverage | apps/web/src/ | - | Add Vitest + Testing Library tests | Open
T-007 | LOW | Testing | Coverage | No load/performance tests | No way to verify performance under load | - | - | Add k6 or Artillery load tests | Open

## Fix Plan
Phase | Sprint | Task | Issues Addressed | Effort (hours) | Dependencies | Acceptance Criteria
Phase 1: Unblock Build | Sprint 1 | Fix platform dependencies | B-001, B-002 | 1 | None | pnpm install succeeds on target platform
Phase 1: Unblock Build | Sprint 1 | Fix Prisma schema & generate | B-003, B-004 | 2 | B-001 | npx prisma validate passes, client generated
Phase 1: Unblock Build | Sprint 1 | Fix all TypeScript errors | B-005 to B-014 | 4 | B-003 | npx tsc --noEmit exits with 0
Phase 1: Unblock Build | Sprint 1 | Fix missing module import | B-010 | 1 | B-003 | pool.service.ts imports resolve correctly
Phase 1: Unblock Build | Sprint 1 | Verify full build succeeds | - | 1 | All Phase 1 | npm run build completes without errors
Phase 2: Critical Security | Sprint 2 | Remove hardcoded credentials | S-001, S-002, S-003 | 2 | Phase 1 | No hardcoded secrets in codebase (grep clean)
Phase 2: Critical Security | Sprint 2 | Fix SQL injection in buyer-pool | S-004 | 2 | Phase 1 | All SQL uses parameterized queries
Phase 2: Critical Security | Sprint 2 | Secure admin reset endpoint | S-005 | 2 | Phase 1 | Endpoint disabled in prod or behind strong auth
Phase 2: Critical Security | Sprint 2 | Fix XSS vulnerabilities | S-006, F-002 | 1 | Phase 1 | All dangerouslySetInnerHTML uses DOMPurify
Phase 2: Critical Security | Sprint 2 | Harden CSP and security headers | S-007 | 2 | Phase 1 | Security scan passes with no critical findings
Phase 2: Critical Security | Sprint 2 | Fix Cloud Run auth | S-008 | 2 | Phase 1 | API requires authentication at gateway level
Phase 2: Critical Security | Sprint 2 | Fix timing attack vulnerability | S-009 | 1 | Phase 1 | Token comparison uses crypto.timingSafeEqual
Phase 2: Critical Security | Sprint 2 | Tighten rate limiting | S-011, S-012 | 2 | Phase 1 | Auth limited to 15 attempts/15min, admin routes limited
Phase 3: Backend Fixes | Sprint 3 | Add auth to unprotected endpoints | A-001, A-002, A-003, A-004 | 4 | Phase 2 | All endpoints require appropriate authentication
Phase 3: Backend Fixes | Sprint 3 | Add error handling to all routes | A-005 | 4 | Phase 1 | All async handlers wrapped in try-catch
Phase 3: Backend Fixes | Sprint 3 | Add input validation (Zod) | A-006, A-007 | 6 | Phase 1 | All POST/PUT routes validate input with Zod
Phase 3: Backend Fixes | Sprint 3 | Fix performance issues | A-008, D-012 | 2 | Phase 1 | Hard limits on all queries, no unbounded fetches
Phase 3: Backend Fixes | Sprint 3 | Replace any types | A-009 | 4 | Phase 1 | No any types in route handlers
Phase 3: Backend Fixes | Sprint 3 | Add org isolation middleware | A-010 | 4 | Phase 2 | All data queries scoped to user organization
Phase 3: Backend Fixes | Sprint 3 | Standardize error responses | A-011 | 2 | Phase 1 | All errors follow consistent JSON format
Phase 4: Database | Sprint 4 | Add missing indexes | D-001 to D-006, D-010 | 3 | Phase 1 | All critical queries use indexes (EXPLAIN shows index scan)
Phase 4: Database | Sprint 4 | Fix broken foreign keys | D-004, D-007, D-008 | 3 | Phase 1 | All relations have proper FK constraints
Phase 4: Database | Sprint 4 | Add field validation | D-009 | 2 | Phase 3 | Contact fields validated at app and DB level
Phase 4: Database | Sprint 4 | Standardize timestamps | D-011 | 2 | Phase 1 | All date fields use DateTime type consistently
Phase 5: Frontend | Sprint 5 | Fix hardcoded localhost | F-001 | 1 | Phase 1 | App works on any domain
Phase 5: Frontend | Sprint 5 | Fix accessibility issues | F-003, F-004, F-006, F-013 | 2 | Phase 1 | All images have descriptive alt text
Phase 5: Frontend | Sprint 5 | Remove console.log from prod | F-005, A-012 | 1 | Phase 1 | No console.log in production bundle
Phase 5: Frontend | Sprint 5 | Fix SPA navigation | F-007, F-008 | 1 | Phase 1 | All navigation uses Wouter (no full page reloads)
Phase 5: Frontend | Sprint 5 | Replace alert() with toast | F-009 | 1 | Phase 1 | All user feedback uses toast notifications
Phase 5: Frontend | Sprint 5 | Fix memory leaks | F-010 | 1 | Phase 1 | Object URLs cleaned up in useEffect
Phase 6: Infrastructure | Sprint 6 | Add Docker health check | I-001 | 1 | Phase 1 | Container has HEALTHCHECK instruction
Phase 6: Infrastructure | Sprint 6 | Add security scanning to CI | I-002 | 2 | Phase 1 | npm audit and container scan in pipeline
Phase 6: Infrastructure | Sprint 6 | Pin Docker base image | I-003 | 0.5 | None | Dockerfile uses pinned Node version
Phase 6: Infrastructure | Sprint 6 | Fix pnpm in Docker build | I-004 | 1 | None | Dockerfile uses pnpm install --frozen-lockfile
Phase 6: Infrastructure | Sprint 6 | Encrypt Terraform state | I-005 | 2 | None | Remote backend with encryption configured
Phase 6: Infrastructure | Sprint 6 | Fix ESLint for TypeScript | I-006 | 1 | None | ESLint checks .ts/.tsx files
Phase 7: Testing | Sprint 7 | Add auth/RBAC unit tests | T-001, T-003 | 8 | Phase 3 | 80%+ coverage on auth and RBAC modules
Phase 7: Testing | Sprint 7 | Add API integration tests | T-004 | 8 | Phase 3 | All API routes have integration tests
Phase 7: Testing | Sprint 7 | Expand E2E test suite | T-002 | 6 | Phase 5 | E2E covers auth, CRUD, error scenarios
Phase 7: Testing | Sprint 7 | Fix test infrastructure | T-005 | 2 | Phase 1 | Test setup with proper mocks and fixtures
Phase 7: Testing | Sprint 7 | Add frontend component tests | T-006 | 8 | Phase 5 | Critical components have test coverage